## Sheet1
Week | Day | Category | Task | Description | Date of Completion
1 | 1 | Frontend | React Setup | Initialize a React project. Build a drag-and-drop file upload UI for documents. | 2026-06-04
1 | 2 | Backend | FastAPI Basics | Build a Python FastAPI backend with a POST endpoint that receives an image and saves it to a local folder. | 2026-05-05
1 | 3 | Fullstack | API Integration | Connect the React frontend to the FastAPI backend. Display a 'Success' toast notification after upload. | 2026-05-05
1 | 4 | Architecture | Flat-file Storage | Implement a JSON-based metadata system to track uploaded files instead of using a SQL database. | 2026-05-05
1 | 5 | Review | GitOps Workflow | Push code to GitHub. Set up a basic README.md for the project documentation. | 2026-05-06
2 | 1 | CV | OpenCV Environment | Set up OpenCV in the Python backend. Create a route that returns a grayscale version of the uploaded image. | 2026-05-06
2 | 2 | CV | Image Normalization | Implement perspective correction (deskewing) for photographed documents using contour detection. | 2026-05-06
2 | 3 | CV | Adaptive Thresholding | Apply binarization techniques to clean up noisy document backgrounds for better OCR readability.
2 | 4 | CV | UI Visualization | Update the React UI to show side-by-side 'Original' vs 'Processed' images after an upload.
2 | 5 | Review | Optimization | Refactor the image processing pipeline into a reusable Python class/module.
3 | 1 | AI/OCR | Tesseract/EasyOCR | Integrate EasyOCR into the backend to extract raw text from processed document images.
3 | 2 | AI/NLP | Structured Extraction | Use Regex or basic NLP to find specific fields (e.g., Name, ID Number) in the raw OCR text.
3 | 3 | AI/ML | LLM Refining | Integrate Gemini API to take messy OCR text and output a clean JSON object.
3 | 4 | Frontend | Dynamic Forms | Build a React form that auto-populates with the JSON data returned from the AI pipeline.
3 | 5 | Review | End-to-End Demo | Demonstrate a full flow: Upload ID -> Process Image -> Extract Data -> Fill Form.